## Requirements
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No.
1 | Write the story for 6 total levels | 5 | 1 | 1
2 | Storyboard Ideas | 5 | 1 | 1
3 | Initial Architecture Document | 3 | 1 | 1
4 | Make at least 3 Architecture Document Diagrams | 3 | 1 | 1
5 | Sprint 1 Requirements | 2 | 1 | 1
6 | Sprint 1 Requirements Artifacts | 2 | 1 | 1
7 | Updated Agile Reference Stories spreadsheet | 1 | 1 | 1
8 | Peer Evalutation 1 | 1 | 1 | 1
9 | Updated Requirements Stack spreadsheet | 1 | 1 | 1
10 | Sprint 1: GitHub link for Sprint Release | 1 | 1 | 1
11 | Keep Github up to date for sprint 1 submission | 1 | 1 | 1
12 | Skip through dialoges to get to inventory | 2 | 1 | 1
13 | Create pixel art for level 2 | 5 | 1 | 1
14 | Create game logic for level 2 | 8 | 1 | 1
15 | Sprint 2: Updated Requirements Stack spreadsheet | 1 | 2 | 2
16 | Sprint 2: Next Sprint Requirements Artifacts | 2 | 2 | 2
17 | Sprint 2: GitHub link for Sprint Release | 1 | 2 | 2
18 | Peer Evalutation 2 | 1 | 2 | 2
19 | Keep Github up to date for sprint 2 submission | 1 | 2 | 2
20 | Find placeholder assets | 2 | 1 | 2
21 | Spint 2 presentation video | 8 | 2 | 2
22 | Make room layout mockups | 5 | 2 | 2
23 | Make Save Feature | 3 | 1 | 2
24 | Make Mission Control Center Level - find the launch code | 8 | 1 | 2
25 | Make ISS Level - Game ends when you make it to the space station (further levels can be done in 582) | 5 | 1 | 2
26 | Make Moon/other planet Level | 5 | 1 | 2
27 | Make and design Mars Level | 5 | 2 | 2
28 | Make Solar system (for world travel) selection | 5 | 2 | 3
29 | Create pixel art for level 3 | 5 | 2 | 3
30 | Create game logic for level 3 | 5 | 2 | 3
31 | Outline game design for characters and backgrounds | 5 | 3 | 3
32 | Draft Presentation Video script and idea | 8 | 3 | 3
33 | Sprint 3: Updated Requirements Stack spreadsheet | 5 | 2 | 3
34 | Sprint 3: Next Sprint Requirements Artifacts | 8 | 2 | 3
35 | Sprint 3: GitHub link for Sprint Release | 5 | 2 | 3
36 | Peer Evalutation 3 | 3 | 2 | 3
37 | Keep Github up to date for sprint 3 submission | 1 | 3 | 3
38 | Create pixel art for level 4 | 2 | 3 | 3
39 | Create game logic for level 4 | 1 | 3 | 3
40 | Sprint 4: Updated Requirements Stack spreadsheet | 1 | 3 | 3
41 | Sprint 4: Next Sprint Requirements Artifacts | 2 | 3 | 3
42 | Sprint 4: GitHub link for Sprint Release | 5 | 2 | 3
43 | Sprint 4: Peer evaluation | 3 | 2 | 3
44 | Sprint 5: Updated Requirements Stack spreadsheet |  | 2 | 3
45 | Sprint 5: Next Sprint Requirements Artifacts | 3 | 2 | 4
46 | Sprint 5: GitHub link for Sprint Release | 5 | 2 | 4
47 | Peer Evalutation 4 | 5 | 3 | 4
48 | Keep Github up to date for sprint 4 submission | 1 | 3 | 4
49 | Sprint 5: Updated Requirements Stack spreadsheet | 1 | 3 | 4
50 | Sprint 5: Next Sprint Requirements Artifacts | 1 | 3 | 4
51 | Keep Github up to date for sprint 5 submission | 1 | 3 | 4
52 | GitHub link for Sprint 5 Release | 1 | 3 | 5
53 | Final Sprint: Updated Requirements Stack spreadsheet | 3 | 3 | 5
54 | Final Sprint: Sprint Requirements Artifacts | 1 | 4 | 5
55 | Keep Github up to date for Final Sprint submission | 2 | 4 | 5
56 | GitHub link for Final Sprint Release | 2 | 4 | 5
57 | Talk to Karla about getting funding to put on Steam | 1 | 4 | 6
58 | Go through Steam game application process | 5 | 4 | 6
59 | Create Steam game storefront page | 5 | 4 | 6
60 | Replace all placeholder assets before releasing on Steam | 5 | 4 | 6

## Reference Stories
Reference Story No. | Story Pool | Story Source | Summary (25-50 words)
1 | 1 | EECS 581 Capstone | Create a GitHub repository for our capstone project and share access with all team members. This included sending the invite link to all developers and initializing an empty branch.
2 | 1 | EECS 581 Capstone | Installed and configured the Godot game engine on computers to prepare the project environment. Verified installation and confirmed the engine could successfully create and run projects.
3 | 1 | EECS 581 Project 2 | Allow the player to choose how many mines there should be when playing Minesweeper. This checks that the user has entered a valid number between 10 and 20
4 | 2 | EECS 581 Project 1 & 2 | Set up person hours tracker. Come up with required criteria (estimated time vs actual time, description of task, who the task is assigned to) and implement them in a Google spreadsheet
5 | 2 | EECS 581 Capstone | Hold weekly Scrum meetings to review completed tasks, discuss progress, identify blockers, and align on project priorities. During each meeting, set clear goals for the next sprint and assign responsibilities to team members to ensure tasks are completed before the next session.
6 | 2 | EECS 581 capstone | Schedule and coordinate weekly meeting times for both team and TA sessions,making sure all memebers are present for a one-hour meeting each week at a common, agreed-upon time.
7 | 3 | EECS 581 Project 2 | Add buttons to the main menu allowing the player to select whether to play solo, take turns with an AI, or have the AI auto solve. This also includes adding buttons to select which game mode the AI plays on: easy, medium, or hard.
8 | 3 | EECS 581 Project 2 | Create a high-level system architecture document detailing the core game components, AI logic layers, and interactions between various game systems to ensure clarity, organization, and efficient team collaboration.
9 | 3 | EECS 581 Project 2 | Create Easy AI functionality that enables the computer to randomly select and uncover a cell that has not already been revealed or flagged, ensuring basic automated gameplay without using any strategic decision-making or pattern recognition
10 | 5 | EECS 581 Capstone | Developed UML diagrams for the architecture documentation to illustrate how each component of the Interstellern game operates. The documentation included system component diagrams, detailed design visuals, a clear project overview, and step-by-step gameplay instructions.
11 | 5 | EECS 581 Project 2 | Create Medium AI functionality. Allows computer to select a cell to uncover based on two strategies and it's memory, only resorting to a random choice when out of choices.
12 | 5 | EECS 581 Project 2 | Implement additional game components, this includes a reply button, a reset feature and visual idicators that show whether it is the AI's turn or the players turn.
13 | 8 | EECS 581 Project 2 | Create the 10x10 grid (rows and columns) and randomly place a set number of mines. Ensure that mines are placed within bounds and do not overlap (each cell can only contain one mine). After placement, calculate and store the number of adjacent mines for every non mine cell.
14 | 8 | EECS 581 Project 1 | Let the player reveal a cell. Check whether the selected cell contains a mine. If it’s a mine, then game over. If it’s not a mine, then reveal the cell and show the count of nearby mines. If the number is 0, automatically reveal all adjacent non mine cells recursively.
15 | 8 | EECS 581 Project 1 & 2 | Check for win or loss. If player reveals a cell with a mine, then end game, reveal all mines, show “Game Over.” If all non mine cells are revealed, then show “You Win!” message and end game. Check that all mines were either flagged/avoided and all safe cells uncovered.
16 | 8 | EECS 581 Project 1 & 2 | After each reveal, update the game board. Maintain separate data structures for the hidden board (true mine locations and numbers) and visible board (what the player currently sees). Track how many safe cells remain unrevealed.
17 | 8 | EECS 581 Capstone | Designed and implemented the bookshelf puzzle allowing players to rearrange books through interactive clicking mechanics. Integrated the puzzle with inventory rewards and ensured compatibility with other interactable objects and overall game progression.
18 | 13 | EECS 581 Project 2 | Implement hard AI into Minesweeper. This comes up with unique strategies to check if cell should be flagged as mine or uncovered as not mine. This AI dosen't cheat, it had no extra knowledge of game board and all moves were based on the same information the user had.
19 | 13 | EECS 581 capstone | Designed and developed scenes, including interactive NPC dialogues with team members. Integrated character interactions, environment assets, and gameplay flow while ensuring compatibility with puzzles and storyline progression within the Interstellern game
20 | 13 | EECS 678 Quash Project | Unit testing to check every part of the shell program to make sure it works like a real UNIX shell. It tests commands, redirection, pipelines, job control, and error handling to confirm everything runs correctly, handles mistakes properly, and responds the way users would expect in different situations.