## Requirements
Requirement ID | Description of Requirement | Story Points | Priority | Sprint No. | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 20 | Column 21 | Column 22 | Column 23 | Column 24 | Column 25 | Column 26
1 | Set up Git Repo | 1 | 1
2 | Set up Godot | 1 | 1
3 | Integrate Git to Gadot | 1 | 1
4 | Get familiar with Godot and decide which language to use (C++, C#, python-like godot language) | 1 | 1
5 | Make title screen | 2 | 1
6 | Find placeholder assets | 2 | 1
7 | Write the story - go down the intern route | 5 | 1
8 | Make Save Feature | 8 | 1
9 | Make game character sprite | 5 | 1
10 | Make room assets | 5 | 1
11 | Make Laboratory Level - find the password for classified files | 5 | 2
12 | Make Mission Control Center Level - find the launch code | 5 | 2
13 | Make ISS Level - Game ends when you make it ot the space station (further levels can be done in 582) | 5 | 2
14 | Make Moon/other planet Level | 5 | 2
15 | Make and design Mars Level | 5 | 3
16 | Make Solar system (for world travel) selection | 8 | 3
17 | Make/find music | 8 | 2
18 | Make/find sound effects | 5 | 2
19 | Integrate Music and Sound Effects to game | 5 | 2
20 | Outline game design for characters and backgrounds | 5 | 2
21 | Initial Architecture Document | 3 | 1
22 | Make at least 3 Architecture Document Diagrams | 3 | 1
23 | Sprint 1 Requirements | 3 | 1
24 | Draft Presentation Video script and idea | 3 | 2
25 | Sprint 1 Requirements Artifacts | 2 | 2
27 | Updated Agile Reference Stories spreadsheet | 1 | 1
28 | Updated Requirements Stack spreadsheet | 1 | 1
29 | Sprint 1: GitHub link for Sprint Release | 1 | 1
30 | Keep Github up to date for sprint 1 submission | 2 | 1
31 | Sprint 2: Updated Requirements Stack spreadsheet | 1 | 2
32 | Sprint 2: Next Sprint Requirements Artifacts | 2 | 2
33 | Sprint 2: GitHub link for Sprint Release | 1 | 2
34 | Keep Github up to date for sprint 2 submission | 1 | 2
35 | Sprint 3: Updated Requirements Stack spreadsheet | 1 | 3
36 | Sprint 3: Next Sprint Requirements Artifacts | 2 | 3
37 | Sprint 3: GitHub link for Sprint Release | 1 | 3
38 | Keep Github up to date for sprint 3 submission | 2 | 3
39 | Final Sprint: Updated Requirements Stack spreadsheet | 1 | 4
40 | Final Sprint: Next Sprint Requirements Artifacts | 2 | 4
41 | Keep Github up to date for sprint 4 submission | 2 | 4
42 | GitHub link for Final Sprint Release | 1 | 4
43 | Final Sprint Presentation Video | 5 | 4

## Reference Stories
Reference Story No. | Story Pool | Story Source | Summary (25-50 words) | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16 | Column 17 | Column 18 | Column 19 | Column 20 | Column 21 | Column 22
1 | 1 | EECS 581 Project 1 & 2 | Setup Github repository. Invite the entire team to be collaborators on the repo. Ensure everyone is able to clone the repo and has write access.
2 | 1 | EECS 168 | Create Hello World program in Python. This program simply prints "Hello World" to the command line when run. It is used to demonstrate basic knowledge of the programming language.
3 | 1 | EECS 581 Project 2 | Allow the player to choose how many mines there should when playing Minesweeper. This checks that the user has entered a valid number between 10 and 20
4 | 2 | EECS 581 Project 1 & 2 | Set up person hours tracker. Come up with required criteria (estimated time vs actual time, description of task, who the task is assigned to) and implement them in a Google spreadsheet
5 | 2 | EECS 581 Project 1 & 2 | Hold weekly scurm meeting to discuss what we completed, any blockers/impediments and next sprint goals. Assign tasks to be completed by the next meeting.
6 | 2 | EECS 581 Project 1 & 2 | Coordinating weekly meeting times for team and TA meetings. Ensuring everyone is consistently avalible at a common time each week for 1 hour.
7 | 3 | EECS 581 Project 2 | Add buttons to the main menu allowing the player to select whether to play solo, take turns with an AI, or have the AI auto solve. This also includes adding buttons to select which game mode the AI plays on: easy, medium, or hard.
8 | 3 | EECS 581 Project 2 | Create a high level system architeure document describing the core game components, AI logic layers, and interactions between the game
9 | 3 | EECS 581 Project 2 | Create Easy AI functionality that enables the computer to randomly select and uncover a cell that has not already been revealed or flagged, ensuring basic automated gameplay without using any strategic decision-making or pattern recognition
10 | 5 | EECS 581 Project 2 | Created UML diagrams for the architecture document explaining how each of the Minesweeper game components work. This included diagrams for the easy move, the medium move, and the hard move logic.
11 | 5 | EECS 581 Project 2 | Create Medium AI functionality. Allows computer to select a cell to uncover based on two strategies and it's memory, only resorting to a random choice when out of choices.
12 | 5 | EECS 581 Project 2 | Implement additional game components, including a reply button, reset feature and visual idicators showing whether it is the AI's turn or the players turn.
13 | 8 | EECS 581 Project 2 | Create the 10x10 grid (rows and columns) and randomly place a set number of mines. Ensure that mines are placed within bounds and do not overlap (each cell can only contain one mine). After placement, calculate and store the number of adjacent mines for every non mine cell.
14 | 8 | EECS 581 Project 1 | Let the player reveal a cell. Check whether the selected cell contains a mine. If it’s a mine, then game over. If it’s not a mine, then reveal the cell and show the count of nearby mines. If the number is 0, automatically reveal all adjacent non mine cells recursively.
15 | 8 | EECS 581 Project 1 | Create UI Mockup of different game state screens using Figma. Mock the game state flow and account for the user winning or losing the game.
16 | 8 | EECS 581 Project 1 & 2 | After each reveal, update the game board. Maintain separate data structures for the hidden board (true mine locations and numbers) and visible board (what the player currently sees). Track how many safe cells remain unrevealed.
17 | 8 | EECS 581 Project 1 & 2 | Check for win or loss. If player reveals a cell with a mine, then end game, reveal all mines, show “Game Over.” If all non mine cells are revealed, then show “You Win!” message and end game. Check that all mines were either flagged/avoided and all safe cells uncovered.
18 | 13 | EECS 581 Project 2 | Implement hard AI into Minesweeper. This comes up with unique strategies to check if cell should be flagged as mine or uncovered as not mine. This AI dosen't cheat, it had no extra knowledge of game board and all moves were based on the same information the user had.
19 | 13 | EECS 581 Project 1 | Integrate a Minesweeper class into the front end using Tkinter, which will connect the backend game logic with the game's visual components to ensure an enjoyable user experience.
20 | 13 | EECS 678 Quash Project | Unit testing to check every part of the shell program to make sure it works like a real UNIX shell. It tests commands, redirection, pipelines, job control, and error handling to confirm everything runs correctly, handles mistakes properly, and responds the way users would expect in different situations.